## Slide 1: BGC Roadmap April 1 to June 30
Susannah Burrows (deputy), Kate Calvin (lead)

## Slide 2: BGC Roadmap
Roadmap is for the next 3 months.
Our epics are all pretty long time horizon, so there is little difference between the annual roadmap and the quarterly roadmap.
Kate has been resetting start dates on epics so they don’t show up in the reporting unless they should have begun.

## Slide 3: Simulations & Analysis
Task | Lead
Complete v1 CBGC simulations, including diagnostics and tracking/managing allocations | Katherine Calvin
Complete v1 CBGC simulation with ocean BGC | Mathew Maltrud
Prognostic CO2 simulations | Bryce Harrop
Analysis of ocean BGC in phase 1 simulations | Nicole Jeffery
Analysis of land BGC for CTC in phase 1 simulations | Peter Thornton
Analysis of land BGC for ECA in phase 1 simulations | Qing Zhu

## Slide 4: Papers
Paper | Lead
Paper: The implications of structural uncertainty on carbon cycle dynamics | Ben Bond-Lamberty
Paper: Plant and soil responses under different BGC scenarios | William Riley
Paper: Analysis of BGC impacts on atmospheric dynamics | Bryce Harrop
Paper: MPAS-O in the CBGC v1 simulations | Nicole Jeffery
Paper: Implications of Phosphorous on the carbon cycle | Peter Thornton
Paper: Nutrient limitations on the carbon cycle | Qing Zhu
Paper: Description of the E3SM v1 BGC model | Susannah Burrows

## Slide 5: Coordination
Task | Lead
Track U. Illinois project and keep BGC group informed of relevant developments | Katherine Calvin
Track Hess project and keep BGC group informed of relevant developments | Katherine Calvin
Track Moore project and keep BGC group informed of relevant developments | Mathew Maltrud
Track Gnanedesikan and keep BGC group informed of relevant developments | Mathew Maltrud
Track Mahowold project and keep BGC group informed of relevant developments | Yan Feng
Track Chai project and keep BGC group informed of relevant developments | Nicole Jeffery
Track atmosphere NGDs | Hailong Wang
Coordinate BGC webinar | Susannah Burrows

## Slide 6: Coupled Model Development
Task | Lead
Review, test, fix C mass conservation in coupled BGC system | Nicole Jeffery
Implement/validate a compset with dynamic CO2 ocean-atm coupling, includes fix regridding in atmosphere, fix aircraft emissions, and simulations to evaluate the model | Bryce Harrop

## Slide 7: Energy
Task | Lead
Paper: complete paper on impact of initial land conditions in iESM | Alan Di Vittorio
Paper: complete paper on iESM45 vs 85 | Katherine Calvin
Paper: Investigating the CO2 radiative and physiological effects and human intervention on water cycle | Xiaoying Shi
Actionable science metrics | Katherine Calvin
Couple GCAM with E3SM | Tim Shippert
Update to latest version of GCAM | Katherine Calvin
Couple temperature to GCAM building sector | Tim Shippert

## Slide 8: Land
Task | Lead
Land surface data sets for the high res SSP5-85 and the SSP5-34 | Louise Parsons Chini
Documentation for land surface data set processing | Louise Parsons Chini
Paper: dynamic planting dates | Beth Drewniak
Surface data sets for crops that work with the dynamic land units | Beth Drewniak
Dynamic land units | Gautam Bisht
Integrate dynamic planting date code into ELM | Beth Drewniak
Update parameters for existing crops | Beth Drewniak
FATES - global parameterization | Jennifer Holm
Test the incorporation of ECA features into ELM v2 | Qing Zhu
Develop a plan for incorporating ECA features into ELM v2 | Ben Bond-Lamberty
Paper: ELM v1 simulations over the amazon | Xiaojuan Yang
Paper: Global ELM v1 simulations | Xiaojuan Yang
UQ in FATES | Khachik Sargsyan
UQ with crops | Khachik Sargsyan

## Slide 9: Ocean, Ice, and Atmosphere
Task | Lead
Evaluate MARBL versus MPAS-O treatments of ocean BGC | Nicole Jeffery
Improvements to MARBL (e.g., DMS-specific phytoplankton, organic macromolecules) | Mathew Maltrud
Testing, validation of black carbon, dust on sea ice in coupled model | Nicole Jeffery
Make consistent dynamic dust deposition to ocean over polar regions | Nicole Jeffery
Correct transient nitrate deposition to ocean | Mathew Maltrud
Fix mass conservation bug | Bryce Harrop